## Sheet1
Top 5 dependencies
#
| 1 Pose and tracking source (Tracker → YOLO-Pose) | Per-player 2D keypoints @ 50 Hz with stable track_id, camera_id, and ms timestamps. Use NTU-25 joints (or 17??) so we match the pretrain + graph config. Missing joints probably conf=0. We can store pixel coords, the model’s data_bn handles normalization (scale to 0 – 1 in the feeder??). Mock pose streamer that replays 10–60 s segments and can deliberately flip track_ids to simulate ID switches.
| 2 Storage & graph schema (Memgraph “property graph”) | We need to assemble the last T frames for one player fast into (C,T,V,M) for serving. Sketch: (:Player)-[:HAS_POSE]->(:Pose{t,track_id,keypoints,conf,v=25/17}), (:Pose)-[:NEXT]->(:Pose), (:Player)-[:PERFORMS]->(:Action{class,p,t_start,t_end}). Add index on (Pose.track_id, Pose.t) and a rolling retention (e.g., last 20 s). Mock: seed 10–60 s synthetic poses + :NEXT.
| 3 Model input format & feeder (NPZ + feeder_football.py) | HD-GCN doesn’t read video, it wants an NPZ with x shaped (N,T,V,C,M) and y one-hot. Freeze: V=25/17, C=3 (x,y,conf), M=1, T=64, pad/crop clips to T. Ship a tiny NPZ builder and a minimal feeder_football.py so training can start before the live pipe.
| 4 Labels & annotation (CVAT + policy) | Start with ~30 min (??) seed clips for few core actions, labeled per-player with t_start/t_end. Export CSV/JSON {track_id, start_frame, end_frame, class}, converter writes one-hots into the NPZ. Try to keep simple, consistent boundary rules (± a few frames) so fine tuning is stable.
| 5 Pretrained weights + fine-tune + serving contract | Download NTU-RGB+D 120 HD-GCN weights and set ignore_weights: [fc.weight, fc.bias]. Fine-tune config: num_class=?, num_point=25/17, num_person=1, window_size=?, LR ≈ ??. Expose a small POST /classify that receives a (C,T,V,M) skeleton window for one player, runs HD-GCN, and logs the most probable action to Memgraph. After it works, add smoothing (hysteresis + event merging) so detections are stable..